## Sheet1
Responsibility Priority 1 = Primary Responsibility 2 = Secondary Responsibility 3 = Information Only
PRE-PLANNING PHASE PHASE
|  | RESPONSIBILITY (Assign #'s) |  |  |  | BARRIER | CONTROL | ACCEPTANCE
NO. | SCHEDULE ACTIVITY | OWNER | ARCH | CM | DATE | DESCRIPTION | DESCRIPTION | OWNER | ARCH | CM | DATE
1 | Initiate Project Concept
2 | Select Architect
3 | Issue Architect Contract
4 | Establish Team Representatives
5 | Establish Communications Procedures
6
7
8
9
10
sandtrapper.com
Responsibility Priority 1 = Primary Responsibility 2 = Secondary Responsibility 3 = Information Only
CONCEPTUAL PLANNING PHASE
|  | RESPONSIBILITY (Assign #'s) |  |  |  | BARRIER | CONTROL | ACCEPTANCE
NO. | SCHEDULE ACTIVITY | OWNER | ARCH | CM | DATE | DESCRIPTION | DESCRIPTION | OWNER | ARCH | CM | DATE
1 | Establish Overall Project Budget
2 | Develop Environmental Program/Review Impact
3 | Conduct Course Review/Evaluation
4 | Review Existing Irrigation/Drainage Network
5 | Coordinate with Government Agencies (if necessary)
6 | Evaluate Financial Feasibility
7 | Develop Conceptual Estimate
8 | Evaluate Budget vs. Estimate
9 | Perform Process Hazzards Review
10
sandtrapper.com
Responsibility Priority 1 = Primary Responsibility 2 = Secondary Responsibility 3 = Information Only
SCHEMATIC DESIGN PHASE
|  | RESPONSIBILITY (Assign #'s) |  |  |  | BARRIER | CONTROL | ACCEPTANCE
NO. | SCHEDULE ACTIVITY | OWNER | ARCH | CM | DATE | DESCRIPTION | DESCRIPTION | OWNER | ARCH | CM | DATE
1 | Prepare Design Schedule
2 | Recommend Basic Materials & Systems
3 | Prepare Schematic Dawings
4 | Prepare Outline Specifications
5 | Retain Secial Consultants
6 | Analyze Alternate Systems
7 | Conduct Constructability Analysis
8 | Conduct Quality Review Meeting
9 | Establish Reporting Procedures
10 | Develop Bid Package Format
sandtrapper.com
Responsibility Priority 1 = Primary Responsibility 2 = Secondary Responsibility 3 = Information Only
SCHEMATIC DESIGN PHASE (CONTINUED)
|  | RESPONSIBILITY (Assign #'s) |  |  |  | BARRIER | CONTROL | ACCEPTANCE
NO. | SCHEDULE ACTIVITY | OWNER | ARCH | CM | DATE | DESCRIPTION | DESCRIPTION | OWNER | ARCH | CM | DATE
11 | Identify Long Lead Items
12 | Update Conceptual Estimate
13 | Analyze Budget vs. Conceptual Estimate
14 | Update Master Schedule
15 | Establish Required Construction Standards
16
17
18
19
20
sandtrapper.com
Responsibility Priority 1 = Primary Responsibility 2 = Secondary Responsibility 3 = Information Only
DESIGN DEVELOPMENT PHASE
|  | RESPONSIBILITY (Assign #'s) |  |  |  | BARRIER | CONTROL | ACCEPTANCE
NO. | SCHEDULE ACTIVITY | OWNER | ARCH | CM | DATE | DESCRIPTION | DESCRIPTION | OWNER | ARCH | CM | DATE
1 | Confirm & Update Design
2 | Evaluate Aesthetic Concepts
3 | Evaluate Structural & Mechanical Systems
4 | Conclude Value Engineering
5 | Refine Outline Specifications
6 | Complete Design Development Drawings
7 | Prepare Bidders Lst
8 | Update Master Schedule
9 | Analyze Budget vs. Estimate
10 | Refine Program Budget
sandtrapper.com
Responsibility Priority 1 = Primary Responsibility 2 = Secondary Responsibility 3 = Information Only
DESIGN DEVELOMENT PHASE (CONTINUED)
|  | RESPONSIBILITY (Assign #'s) |  |  |  | BARRIER | CONTROL | ACCEPTANCE
NO. | SCHEDULE ACTIVITY | OWNER | ARCH | CM | DATE | DESCRIPTION | DESCRIPTION | OWNER | ARCH | CM | DATE
11 | Prepare Long Lead Purchases
12 | Prepare Financial Appropriation
13 | Prepare Required Site Standards
14 | Conclude Process Hazzards Review
sandtrapper.com
Responsibility Priority 1 = Primary Responsibility 2 = Secondary Responsibility 3 = Information Only
CONTRACT DOCUMENTS PHASE
|  | RESPONSIBILITY (Assign #'s) |  |  |  | BARRIER | CONTROL | ACCEPTANCE
NO. | SCHEDULE ACTIVITY | OWNER | ARCH | CM | DATE | DESCRIPTION | DESCRIPTION | OWNER | ARCH | CM | DATE
1 | Update Design Schedule
2 | Establish On-Site Staffing
3 | Finalize Plans & Specifications
4 | Finalize Construction Estimate
5 | Finalize Project Budget
6 | Arrange & Coordinate Temporary Utilities
7 | Final Review of Contract
8 | Finalize Safety Program
9 | Finalize Bidders List
10 | Review of Insurance Requirements
sandtrapper.com
Responsibility Priority 1 = Primary Responsibility 2 = Secondary Responsibility 3 = Information Only
BIDDING PHASE
|  | RESPONSIBILITY (Assign #'s) |  |  |  | BARRIER | CONTROL | ACCEPTANCE
NO. | SCHEDULE ACTIVITY | OWNER | ARCH | CM | DATE | DESCRIPTION | DESCRIPTION | OWNER | ARCH | CM | DATE
1 | Issue Invitations to Bid
2 | Conduct Pre-Bid Meetings
3 | Receive & Evaluate Bids
4 | Notify Successful & Unsuccessful Bidders
5 | Line Item or Cost Negotiations
6 | Pre-Award Negotiations & Revisions to Bids
7 | Final Selection of Contractor
sandtrapper.com
Responsibility Priority 1 = Primary Responsibility 2 = Secondary Responsibility 3 = Information Only
CONSTRUCTION PHASE
|  | RESPONSIBILITY (Assign #'s) |  |  |  | BARRIER | CONTROL | ACCEPTANCE
NO. | SCHEDULE ACTIVITY | OWNER | ARCH | CM | DATE | DESCRIPTION | DESCRIPTION | OWNER | ARCH | CM | DATE
1 | Issue Purchase Orders
2 | Prepare Submittal Control Logs
3 | Set-Up Construction Field Office
4 | Arrange & Coordinate Temporary Requirements
5 | Review Permit or Environmental Requirements
6 | Establish Site Entry & Exit Locations
7 | Establish Pedestrian or Vehicle Traffic Control
8 | Establish Laydown, Storage, Loading & Unloading Areas
9 | Monitor Progress & Update Schedule
10 | Coordinate Daily Work Activities
sandtrapper.com
Responsibility Priority 1 = Primary Responsibility 2 = Secondary Responsibility 3 = Information Only
CONSTRUCTION PHASE (CONTINUED)
|  | RESPONSIBILITY (Assign #'s) |  |  |  | BARRIER | CONTROL | ACCEPTANCE
NO. | SCHEDULE ACTIVITY | OWNER | ARCH | CM | DATE | DESCRIPTION | DESCRIPTION | OWNER | ARCH | CM | DATE
11 | Conduct Regular or Special Job Meetings
12 | Prepare & Monitor Project Cost Controls
13 | Weekly, BiWeekly, or Monthly Reports
14 | Inspect & Monitor Contractor's Progress
15 | Monitor Work for Design Conformance
16 | Prepare Applications for Payments
17 | Evaluate & Approve Contractor Performance & Schedule Conformity
18 | Prepare & Process Change Orders
19 | Interpret Plans & Specifications
20 | Review Site Safety Conformity
sandtrapper.com
Responsibility Priority 1 = Primary Responsibility 2 = Secondary Responsibility 3 = Information Only
CONSTRUCTION PHASE (CONTINUED)
|  | RESPONSIBILITY (Assign #'s) |  |  |  | BARRIER | CONTROL | ACCEPTANCE
NO. | SCHEDULE ACTIVITY | OWNER | ARCH | CM | DATE | DESCRIPTION | DESCRIPTION | OWNER | ARCH | CM | DATE
21 | Conduct Weekly Staff or Team Meetings
22 | Administer Site Security Program
23 | Prepare Work Procedures for Special Jobs
24 | Conduct Incident Investigations & Reports
25 | Coordinate Delivery/Receipt of Owner Supplied Equipment
26 | Certify Contractor Completion Phases & Document
27 | Prepare Final Cost Accounting Reports
28 | Prepare Project Completion Punch Lists
29 | Complete Project Closeout Notices
sandtrapper.com