PROJECT ORGANIZATION

FILING SYSTEM & PROJECT MANUAL

FILING SYSTEM STRUCTURE

- General Correspondence

- Owner Contract

- Contract Summary

- Insurance Certificates, Bonds

- Roles & Responsibilities

- Payment Requests

- Incentives statusing

- Changes in Owner Contract

- Purchase Orders & Subcontracts

- Insurance Certificates/Bonds

- Payment Log

- Submittals in Process

- Submittals Approved

- Requests for Information in Process

- Requests for Information Finalized

- Engineering Correspondence

- Design Agreement

- Documents Status

- Billings/Payment

- Vendor Files (reports, submittals, evaluations)

  - Mechanical

  - Electrical

- Safety Plan - Meetings, Inspections, & Reports

- Quality Plan - Meetings, Inspections & Reports

- Progress Meetings, Reports

- Cost:	Labor reports

- Equipment & Tool Reports (rentals & expendables)

- PO (Materials)/Contract (Subcontractor) Status Reports

- Field PO's

- Freight & Drayage

- Travel & Miscellaneous (shop visits, off-site meetings)

- Craftworker Recruitment, Training & Incentives

- Consultants (Labs, Form/Shoring Design, etc.)

- Cost to Complete

- Control Estimate

- Schedule Information

- Permits, Authorities, Inspections

- Independent Lab Tests & Reports

- Project Execution Plan

- Performance Criteria: Objectives/Evaluations

PROJECT MANUAL

Purpose:

To maintain a single bound document that includes the essential information for efficient management of production, communications, costs, physical resources, and finances for project success.

Responsibility:

Project Manager

When Required:

Initiate at the start of a project and maintain through completion of the project.

Scope:

See enclosures

Enclosures

The following describes the items, data, material, and information that is to be included in the Project Manual

NOTE:  THIS IS A CONFIDENTIAL DOCUMENT AND IS "NEVER" TO BE TAKEN FROM THE CORPORATE OFFICE UNLESS ALL CONTRACTS AND PRICING INFORMATION IS REMOVED.

Section 1 - Production Control

- Schedule

  - Updated Start Schedule, when applicable

  - Updated Completion Schedule, when applicable

  - Updated Delivery and Installation Schedules

Note:  JOB PROGRESS SCHEDULE WILL REMAIN UPDATED AND POSTED IN THE CONTROL BOOK.

- Meetings

  - Copy of current and previous two Main Office Job Progress Meeting Minutes, with summary sheet on top.

  - Copy of current plus previous two Job Progress Jobsite Subcontractor Meeting Minutes, when applicable.

  - Any other current meeting notes and/or minutes that document or describe problems or situations which may require attention.

- Procurement

  - Updated copy of status of Subcontracts.  Use date of occurrence rather than a check mark to indicate action completed.

Section 2 - Cost Control

- Labor cost information   The summary of labor cost for the most recent and two previous pay periods.

- Materials/Subcontracts Commitment Status   The last month's Purchase Commitment Summary Report.

- Equipment   The current copy of the construction manager's equipment charge report.

- Cost to Complete   The most recent project manager's projected cost to complete summary.

Section 3 - Financial Control

- Invoicing.  A copy of the last invoice submitted to the owner.

- Change order log.  Copy of the current C/O Log

- Construction Cost Code Summary.  Current copy of the Construction Cost Code Summary Report.

- Subcontractor Ledger Summary.  Current copy of S/C Ledger Summary Report

Section 4 - Contracts

- Summary sheets.  Summary of status of each subcontract amount and changes.

- Subcontracts & Purchase Orders.  Alphabetical insertion of P.M.,'s copies of subcontracts, P.O.'s, and bonds.  Each subcontract is to be preceded by the summary sheet.

Section 5 - Documentation:

- Project Manager's Project Summary Sheet (Subcontract Status)

        - Purpose.  To be used as a guide to determine that most major areas of responsibility are being addressed.

        - Responsibility.  Project Manager

        - When Required.  Initially and for project's duration

        - Scope.  Lists significant items, activities and milestones from start through completion of a project.

        - Action required.

          - Review periodically

          - List the date that each area of responsibility is completed.

          - Get results and do not procrastinate.

        - Forms:  Project Control List

- Document control logs

- Requests and Changes Log

- Contract and P.O. Log.

- Submittals Log